## UCP
Paquete | Puntos de Caso de Uso - Use Case Points
Unadjusted Use Case Points:
Análisis de Actores
Complejidad | Definición | Peso | Cantidad | Peso Total
Simple | Representa otro sistema con una interfase definida de aplicación programada | 1 | 2 | 2
Promedio | Interactúa con otra aplicación a través de un protocolo o interacción humana a través de terminal de línea | 2 | 3 | 6
Complejo | Interacción humana a través de interfase usuario gráfica | 3 | 0 | 0
TOTAL |  |  | 5 | 8
Análisis de Casos de Uso
Complejidad | Definición | Peso | Cantidad | Peso Total
Simple | Tiene 3 o menos transacciones incluyendo cursos alternativos. Casos de uso con menos de 5 objetos de análisis | 5 | 6 | 30
Promedio | Tiene 3 a 7 transacciones incluyendo cursos alternativos. Casos de uso con 5 a 10 objetos de análisis | 10 | 23 | 230
Complejo | Tiene más de 7 transacciones incluyendo cursos alternativos. Casos de uso con más de 10 objetos de análisis | 15 | 4 | 60
TOTAL |  |  | 33 | 320
Total de Unadjusted Case Points |  |  |  | 328
Adjusted Use Case Points: AUCP = UUCP × TCF × EF |  |  |  | 316.3478
Esfuerzo Estimado en horas: AUCP x 8 |  |  |  | 2530.7824 | Hs. | 15.0642 | meses/hombre
| Fases: |  |  |  |  | Precio x Hora
Analista | Especificación |  | 5% | 126.5391 | Hs. | 400 | 50615.648
| Análisis |  | 10% | 253.0782 | Hs. | 400 | 101231.296
AnalistaProgr | Diseño |  | 10% | 253.0782 | Hs. | 700 | 177154.768
Programador | Construcción |  | 50% | 1265.3912 | Hs. | 300 | 379617.36
Soporte | Integración |  | 5% | 126.5391 | Hs. | 200 | 25307.824
Tester | Pruebas |  | 15% | 379.6174 | Hs. | 200 | 75923.472
Lider | Administración |  | 5% | 126.5391 | Hs. | 1000 | 126539.12
|  |  | 100% | 2530.7824 | Hs. |  | 936389.488

## TCF
Factor de Complejidad Técnica -Technical Complexity Factor (TCF)
Factor | Descripción | Peso | Valor Asig. | Factor Calc | Comentarios
T1 | Sistema Distribuido | 2 | 0 | 0 | Central system
T2 | Tiempo de Respuesta, objetivos de performance | 1 | 3 | 3 | Speed is probably limited by human input
T3 | Eficiencia de Usuario Final | 1 | 5 | 5 | Needs to be efficient
T4 | Complejidad de procesamiento interno | 1 | 1 | 1 | No complex calculations
T5 | Codigo debe ser reusable | 1 | 2 | 2 | Code fragments should be reused
T6 | Easy to install | 0.5 | 0 | 0 | There is no need to have an installation process
T7 | Easy to use | 0.5 | 5 | 2.5 | Very user-friendly
T8 | Portable | 2 | 0 | 0 | No
T9 | Easy to change | 1 | 4 | 4 | Low maintenance cost
T10 | Concurrent | 1 | 0 | 0 | No
T11 | Includes special security objectives | 1 | 3 | 3 | Normal security
T12 | Provides direct access for third parties | 1 | 5 | 5 | WEB users have direct access
T13 | Special user training facilities are required | 1 | 1 | 1 | Few internal users, easy to use system
Total Technical factor (Tfactor): |  |  |  | 26.5
0.865

## EF
Factor de Entorno -Environment Factor (EF)
| Factor | Descripción | Peso | Valor Asig. | Factor Calc | Comentarios
| E1 | Familiar with the project model that is used | 1.5 | 1 | 1.5 | Most staff is not familiar with the model
| E2 | Application experience | 0.5 | 3 | 1.5 | Most staff has worked a few years in this applic.
| E3 | Object-oriented experience | 1 | 4 | 4 | Most staff is familiar with OOP
| E4 | Lead analyst capability | 0.5 | 1 | 0.5
| E5 | Motivation | 1 | 4 | 4 | The team is highly motivated
| E6 | Stable requirements | 2 | 2 | 4 | We expect some changed
| E7 | Part-time staff | -1 | 3 | -3 | Unfortunately several staff is half-time
| E8 | Difficult programming language | -1 | 3 | -3 | Java FX or similar
| Total Environment Factor (Efactor): |  |  |  | 9.5
| EF = 1.4+(-0.03 × EFactor) |  |  |  | 1.115

## Act y CU
Complejidad
| Actores | Baja | Media | Alta
1 | User | 2
2 | Payment Verification Company |  | 1
3 | Admin |  | 2
| Total Actores por Complejidad | 2 | 3 | 0
Complejidad
| Caso de Uso | Baja | Media | Alta
1 | Sign up | 2
2 | Log in | 2
3 | Edit | 2
4 | Delete account |  | 3
5 | Search for Item |  | 3
6 | Add to Cart |  | 2
7 | See Cart |  | 1
8 | Edit Cart |  | 4
9 | Check Out |  |  | 4
10 | Verify Payment |  | 2
11 | Database Management |  | 3
12 | Place Item |  | 2
12 | List of Products |  | 1
13 | Edit List |  | 2
| Total Casos de Uso por Complejidad | 6 | 23 | 4